## Sheet1
Meeting date | Minute Number | Paper Reference | Action Agreed | By Whom | By When | Progress Update | Status
30.03.10 | 1878/10 | WL1780 | Chief Executive's Report: Carers' involvement report presented to Board | Mr Trenchard | Revised date Sept 10 (from Jul 10) | It is proposed to move this to Sept 10 Board to produce a combined paper with Service User Involvement | amber
27.04.10 | 1914/10 | WL1809 | CEO Report Commence auditing the evidence described in the CQC Action Plan | Mr Cubbon | On-going | business cases were being presented at the Ops Board 6 July to request funding from the Invest to Save budget for Programme Manager post | amber
| 1920/10 | WL1815 | Level 1 & 2 Incident Report Update - Q&R Cttee to review Level 1 & 2 Action Plans and report to the Board | Mrs Chapman | 2010-07-01 | completed - see Q&R Cttee Chairs Report in Sept Board paper WL1913 | green
| 1923/10 | WL1820 | Operations board meeting 08.04.10 draft minutes - Look at status of staff and PMVA training within Forensic Services. Forms part of the overview of Mandatory training compliance under taken by the Executive Directors | Mrs Lewis | Revised date to Sept 10 (from Jul 10) | completed | green
25.05.10 | 1944/10 | WL1832 | Chief Executive's Report: Introduce Quarterly reports to monitor the embedded CQC actions | Mr Trenchard | 2010-09-01 | Working with MH Foundation Audit Team. To progress this work | amber
| 1946/10 | WL1840 | Research & Development: Report on the strategic Plan and future | Dr Broughton (Dr Fellow-Smith) | 2010-10-01 |  | amber
29.06.10 | 1983/10 | n/a | Chairman's Report - Board members to receive details re involvement in Oct/Nov 10 visit by MPs to the Trust | Mr McCorkell | 2010-09-01 | see Chairman Report in Sept Board paper WL1902 | amber
| 1984/10 | WL1858 | CEO Report : Decide on the replacement NED for the Trust champion of Safeguarding Children | Mr McCorkell / Mr Cubbon | 2010-09-01 | see Chairman Report in Sept Board paper WL1902 | amber
| 1988/10 | WL1862 | Nursing Strategy: Board to receive report on progress regarding implementation | Mr Trenchard | 2011-01-01 |  | amber
27.07.10 | 2012/10 | WL1858 | CEO Report - Trust Internal Staff Survey (questionnaire) - results published | Mrs Lewis | 2010-08-01 |  | amber
| 2012/10 | WL1858 | CEO Report - Send NEDs more info re NHS London board development conference on 12th Oct 10 | Miss Fadina | 2010-08-01 | actioned | green
| 2014/10 | WL1881 | Mental Health Act Managers Annual Report - benchmark the Trust's discharge numbers against other trusts | Mr Trenchard | 2010-10-01 |  | amber
| 2014/10 | WL1881 | Mental Health Act Managers Annual Report - clarify the duty role of NEDs in an FT | Mr Trenchard | 2010-10-01 |  | amber
| 2014/10 | WL1881 | Mental Health Act Managers Annual Report - provide detail re Lay Managers induction and when the appraisal process will be in place | Mr Trenchard | 2010-09-01 |  | amber
| 2014/10 | WL1881 | Mental Health Act Managers Annual Report - how to appoint vice chair of MH Act Managers Cttee to be agreed | Mr McCorkell / Mrs Chapman | 2010-09-01 | see Chairman Report in Sept Board paper WL1902 | amber
| 2015/10 | WL1882 | IPR - Workforce / HR KPIs - report on Ealing SDU Performance | Mr Cubbon, Mrs Byrne | 2010-09-01 | see CEO Sept Board paper WL(2)1922 | green
| 2015/10 | WL1882 | IPR - Risk: review and ensure all Level 1 risks are on the assurance framework | Mr Trenchard | 2010-09-01 | completed | green
| 2015/10 | WL1882 | IPR - Month 4 July 10 Report - circulate to members in the absence of an August Board meeting | Mrs Byrne | 2010-08-01 | completed - sent to the Board on 27.08.10 | green
| 2016/10 | WL1883 | Level 1 & 2 Incident Report Database - find other ways to achieve the 45 day deadline (other than L2 reports being signed off by IRG instead of the Board) | Mr Trenchard / Mr Cubbon | 2010-10-01 |  | amber
| 2017/10 | WL1884 | PMO Update Report : Board training re the info to be presented in the IPR | Mr Cubbon / Ms Stanion | 2010-09-01 |  | amber
| 2009/10 | WL1885 | Complaints and PALS Annual Report - trend data to be included in next annual report and include in the IPR the top 5 complaints issues | Mr Trenchard | Ongoing |  | amber
| 2019/10 | WL1886 | PPI Annual Report 09/10: carer involvement paper | Mr Trenchard | 2010-09-01 |  | amber
| 2021/10 | WL1888 | Q&R Cttee 17th June 10 minutes / Chairs Report - clarify the difference between not being compliant with NHS firecode and being legally covered | Mrs Byrne | 2010-09-01 |  | amber