## 06 to 07
Yamhill SWCD 2006 - 2007 Annual Workplan and Workload Analysis
ACTION ITEMS |  |  | Workload in Days |  |  | YBC | Other | NRCS | NRCS | SWCD |  | Total
GOAL #1 PROVIDE CONSERVATION ASSISTANCE TO LANDOWNERS. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others | Days
Objective 1: Utilize and develop existing programs.
Participate in Local and Basin USDA Working Groups. | 2 | 1 | 1 | 3 | 2 | 1 |  | 5 | 2 | 1 | 6 | 24
Work with landowners to determine USDA program need. | 4 | 2 |  | 15 | 9 |  |  | 15 | 15 |  | 2 | 62
Provide technical assistance for EQIP Program. | DO: 5; MC: 50; Ken: 70; Kim: 90 |  | 50 | 265
Assist with the implementation and review of CREP plans. | DO: 6; MC: 5; ALF: 12; Ken: 20; Kim: 5 |  | 10 | 58
Utilize Fish and Wildlife funds for Taylor, Wyman, and Balwitt. | TS: 2; DO: 12; MC: 5; JS: X; Ken: x | 0 | 2 | 21
Build working relationship with Grand Rhond Tribe. | TS: 1; DO: 2; ALF: 2; Ken: 2; Kim: 1 |  |  | 8
Utilize OWEB to implement restoration activities for 2 WRP areas and tech support for WRP. | TS: 5; DO: 4; Ken: 6 |  |  | 15
Use NFWF & ODA funds to implement riparian plans. | TS: 2; ALF: 112 |  |  | 114
Complete intital year of raptor enhancement project using WHIP funds. | TS: 4; DO: 5; MC: 10; ALF: 10; Kim: 2 |  | 1 | 32
Provide technical support for CSP landowners. | Ken: 10; Kim: 30 |  | 10 | 50
Unanticapated work related to USDA Programs | 4 | 2 | 2 | 10 | 5 |  |  | 15 | 10 | 1 | 4 | 53
Objective #1 Sub-total | 24 | 5 | 37 | 98 | 152 | 1 | 0 | 143 | 155 | 2 | 85 | 702
Objective 2. Provide non-program related technical assistance and services. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others | Total
Work with landowners to determine need for assistance and refer to other agencies. | 2 | 2 | 5 | 10 | 4 | 4 |  | 10 | 5 | 5 | 4 | 51
Provide site evaluation to cooperators for ponds and wetlands. | 1 |  | 8 | 4 | 1 |  |  | 5 | 5 |  |  | 24
Provide assistance to 10 landowners restoring riparian & wetland areas. | 2 |  | 3 | 4 | 4 | 2 |  | 1 | 1 |  |  | 17
Provide forest management information and technical assistance to 20 landowners. | DO: 8; MC: 2; ALF: 1; Kim: 4 |  |  | 15
Handle walk in and phone requests for service and information from 1800 landowners. | 4 | 10 | 10 | 8 | 4 | X |  | 6 | 5 |  | 10 | 57
Implement native plant distribution program to sell 60,000 plants. | 12 | 12 | 6 | 5 | 5 | 3 |  |  | X |  | 72 | 115
Develop a Willow Cutting block at Miller Woods. | TS: 2; DB: 1; DO: 2; ALF: 1 | 2 | 4 | 12
Expand use of volunteers for district activities. | TS: 3; DB: 3; DO: 2; MC: 2; ALF: 2 |  |  | 12
Record keeping, monthly and quarterly reporting for SWCD & Agencies. | 2 | 4 | 4 | 4 | 4 | 4 |  | 5 | 5 |  |  | 32
Complete Stuckey (ARG)Wetland Project | TS: 2; DO: 4 |  |  | 6
Complete work on DSL funded Hess Creek Project | TS: 1; DO: 5 |  |  | 6
Initiate Wyman Project Phase II. | TS: 2; DO: 5; MC: 3 |  |  | 10
Complete Kroeker Manure Management Project | TS: 1; MC: 4 |  |  | 5
Complete Harlow Manure Storage project | TS: 1; DO: 1; MC: 3 |  |  | 5
Continue oak savanah projects at Cooke and Miller sites | TS: 1; DO: 10; Ken: 1; Kim: 1 | 1 |  | 14
Un-anticipated work involving non-program services and assistance. | 4 | 2 | 8 | 4 | 4 |  |  |  | 4 | 4 | 5 | 35
Objective #2: Subtotal | 40 | 34 | 81 | 53 | 30 | 13 | 0 | 28 | 30 | 12 | 95 | 416
Obj. #3 Seek Funding Sources to provide for staff and project implementation. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others
Develop and manage 6 funding proposals for landowner projects. | TS: 8; ALF: 1; JS: 2; Ken: 1; Kim: 1 |  |  | 13
Administer existing grants to implement restoration projects. | TS: 8; DO: 5; MC: 4 |  |  | 17
Administer existing grant for watershed technical staff through ODA. | [11 empty] | 2 | bar: TS to DB
Research new funding sources, edit applications. | TS: 4; DO: 1; MC: 1; Ken: 1 |  |  | 7
Un-anticipated work involving funding sources and issues. | 4 | 2 | 1 | 1 | 1 |  |  | 1 |  |  |  | 10
Objective #3: Subtotal | 25 | 3 | 6 | 5 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 45
Objective 4. Fulfill role as Noxious Weed Inspectors. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others
Continue to provide for ongoing Meadow Knapweed & knotweed projects. | TS: 2; DB: X; DO: 4 |  |  | 6
Provide assistance in facilitation of control of false brome. | TS: 4 |  |  | 4
Host Weed Committee Meeting & update noxious weed list. | [9 empty] | 1 | 1 | 5 | bar: TS to DO
Encourage biological control agents to be released in Yamhill County. | [11 empty] | 2 | bar: TS; DO
Respond to weed complaints, encourage control, provide tech. assistance. | TS: 3; DO: 3; MC: 2 |  |  | 8
Write and submit 3 articles on weed control for news releases. | TS: 2; DO: 2 |  |  | 4
Continue a knotweed control program. | TS: 1; DO: 3; MC: 4 |  |  | 8
Un-anticipated work involving noxious weed control. | TS: 1; DO: 2; MC: 1 |  |  | 4
Obj. #4 Weed Control Subtotal | 15 | 1 | 16 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 40
Obj. #5 Influence land use in the county through land use reviews and easements. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others
Review & comment on land use planning proposals and activities. | TS: 2; DB: 8 | 7 |  | 17
Complete Friedman Conservation Easement | TS: 3; MC: 1 |  | 2
Complete Hutchison Conservation Eaement | TS: 3; MC: 1 |  | 2 | 6
Complete Chegwynn Family Farm Plan | TS: 4; DO: 1; MC: 1; Ken: 1
Objective #5 Land use Sub-total | 8 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 29
GOAL #1 Totals | 112 | 51 | 140 | 164 | 183 | 16 | 0 | 173 | 186 | 22 | 185 | 1232
ACTION ITEM
GOAL #2 PROVIDE CONSERVATION EDUCATION AND INFORMATION. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others | Total
Obj. #1. Inform the general public through public displays, news articles, internet, etc.
Host the SWCD annual meeting. | 2 | 4 | 1 | 1 | 1 | X |  |  |  | 1 | 1 | 11
Develop and publish newsletter 3 times per year. | 4 | 15 | 4 | 2 | 3 | 3 |  | 1 |  |  | 2 | 34
Select Conservation Cooperator of year. | TS: 1; DB: 1; ALF: 0; Ken: 1 | 2 |  | 5
Provide media w/ news releases, site visits, & background information for articles. | 2 | 2 |  | 1 | 2 | 4 |  | 1 | 1 |  | 1 | 14
Develop and maintain SWCD website. | TS: 1; DB: 5; ALF: 1 |  |  | 7
Obj. #2. Develop Miller Woods as an Educational Venue For Yamhill County
Complete Strategic Plan for Miller Woods. | TS: 4; DO: 5 | 15 | 5 | 29
Complete improvement projects at Miller Woods. | TS: 4; DO: 8; MC: 5 | 5 | 25 | 47
Unanticapated work at Miller Woods | TS: 10; DB: 4; DO: 6; MC: 4; ALF: 1 | 5 | 5 | 35
Obj. #3. Educate school aged citizens. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others | Total
Conduct Woodland Tour outdoor school for over 700 5th graders. | 2 | 8 | 1 | 2 |  | 2 |  | 1 | 1 | 1 | 2 | 20
Develop Miller's Woods Outdoor Center Education Program | 3 | 3 | 3 | 2 |  |  |  | 1 | 1 | 10 | 6 | 29
Speak to school and after school groups | [11 empty] | 1 | bar: TS
Obj. #4. Contact/reach elected officials regarding conservation issues. | [11 empty] | 0
Conduct conservation tour & or luncheon for community leaders, legislators, etc. | [9 empty] | 1 | 4 | 10 | bar: TS to DB; MC to JS
Become involved with the regional water quality committee. | [9 empty] | 1 | bar: TS
Keep county commissioners informed about conservation issues and projects. | TS: 2; DB: 1 |  |  | 3
Obj. #5. Teach landowners through workshops and meetings and educational materials. | [11 empty] | 0
Distribute conservation materials. | 1 | 3 |  | 1 | 1 | X |  | 2 | 1 |  | 1 | 10
Conduct 2 tours of desired land use practices. | 1 | 1 | 1 | 2 | 1 |  |  | 1 |  |  |  | 7
Organize 2 workshops including March Weed Workshop. | 2 | 2 |  | 2 | 2 | 1 |  | 1 |  |  |  | 10
Distribute over 6000 fact sheets to landowners. | DB: 4; MC: 2; ALF: 3 | 1 |  | 10
Obj. #6. Provide outreach to community groups through mailings and presentations. | [11 empty] | 0
Attend community based clubs and organization meetings. | 1 | 3 | 2 | 2 | 2 | 3 |  | 2 | 1 | 2 | 3 | 21
Obj. #7. Maintain a library of conservation related information for staff and public use.
Catalogue all books, videos, and lectures, archive photos and slides, soil maps and info sheets. | DB: 4; MC: 1; ALF: 1 |  | 3 | 9
Un-anticipated work involving education and outreach. | 1 | 3 | 1 | 1 | 4 |  |  | 4 | 1 |  |  | 15
GOAL #2 TOTALS | 44 | 64 | 32 | 29 | 23 | 14 | 0 | 15 | 6 | 44 | 58 | 327
GOAL #3 ACHIEVE SOUND and STABLE DISTRICT OPERATIONS | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others | Total
Establish SWCD direction through annual and long range planning.
Produce an annual work plan & workload analysis. | 3 | 2 | 1 | 1 | 2 | X |  | 1 |  | 5 |  | 15
Finish long range plan for Natural resource concerns. | 1 | 2 | 2 | 1 | 1 | X |  | 1 |  | 12 | 2 | 22
Receive public input into activities, maintain office filing and support. | [11 empty] | 0
Conduct monthly board meetings. Attend Committee meetings, provide agenda/minutes. | 10 | 28 | 8 | 2 | 2 | 1 |  | 1 |  | 32 | 12 | 96
Provide office support to NRCS staff (phones, typing, etc) - supplies, computer support | DB: 10; Ken: 5; Kim: 1 |  |  | 16
Encourage recruitment of Associate Directors and committee members. | 1 |  | 1 | 1 | 0 | X |  | x |  | 20 | 10 | 33
Prepare annual budget, maintain sound accounting practices, annual audit. | [11 empty] | 0
Prepare annual budget, present to budget committee and public. | TS: 10; DB: 4; JS: X | 10 |  | 24
Prepare for and conduct an annual financial audit. | TS: 3; DB: 12 |  |  | 15
Office filing, database maintenance, correspondence, payroll, taxes, accounting. | TS: 1; DB: 30; DO: 5; JS: X |  |  | 36
Maintain professional personnel management practices. | [11 empty] | 0
Maintain policy and procedure manual, insurance, benefits, and safety. | TS: 1; DB: 2; ALF: X | 1 |  | 4
Submit employees for appropriate awards and recognition. | [11 empty] | 1 | bar: TS
Utilize volunteers and partners to complete projects. | TS: 1; DB: 3; ALF: 2; JS: X |  |  | 6
Staff and board participate in OACD meetings (depending on budget). | TS: 3; DB: 3; DO: 1; ALF: 2 | 10 | 10 | 29
Produce staff training plans, provide staff evaluations. | 1 | 4 | 2 |  | 1 | 2 |  | 3 |  | 4 |  | 17
Provide facilities and equipment needed by staff to implement work plans. | [11 empty] | 0
Provide computer upgrades and maintenance. | TS: 1; DB: 5; ALF: X; JS: X |  |  | 6
Provide training if needed at staff and board meetings. | [11 empty] | 4 | bar: TS; ALF; Ken to Kim
Update MOA/MOU's and Policy Statement/Operational Agreements with NRCS. | [11 empty] | 3 | bar: TS to DB; Ken
Develop and implement a plan to aquire a service center | TS: 3 |  |  | 3
Subtotal Objective 3-District Operations | 42 | 106 | 20 | 5 | 11 | 3 | 0 | 13 | 2 | 94 | 34 | 330
GOAL #4 WATERSHED WIDE PLANNING AND PROJECT IMPLEMENTATION. | TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others | Total
1. Administer Yamhill Basin Council, aquire funds for operations and projects.
Yamhill Basin Council Administration and Meetings. | TS: 3; DB: 8; JS: 45; YBC: 40; Ken: 1 | 24 | 4 | 125
YBC Funding/Budgeting and Project Grants. | TS: 2; JS: 40; Ken: 1 |  | 19 | 62
Support development of 2 watershed projects / funding | TS: 1; JS: 30; YBC: 6 |  |  | 37
OWEB/OACD Meeting/Trainings | TS: 4; JS: 6; YBC: 3; Ken: 3 |  |  | 16
2. Conduct water quality monitoring activities in the basin. | [11 empty] | 1 | bar: DO
Monitoring - Stream Temperature and other parameters. | TS: 1; ALF: 1; JS: 20; YBC: 10 |  |  | 32
Implement OWEB funded monitoring program. | JS: 8; YBC: 52 |  |  | 60
Implement WaterWise Education Program with small school systems. | bar: TS; JS
3. Initiate projects with watershed-wide implications. | [11 empty] | 0
Public information / Education Projects, Storm Drain Stenciling. | DB: 1; ALF: 2; JS: 15; YBC: 40 | 10 | 16 | 84
Develop and administer 2 OWEB small grants for project work. | TS: 3; DO: 2; MC: 3; JS: 8; YBC: 5 |  |  | 21
Utilize volunteers and partners to complete projects | TS: 2; DO: 2; JS: 5; YBC: 5 |  |  | 14
Organize and conduct workshops | TS: 3; ALF: 1; JS: 6; YBC: 8 |  |  | 18
4. Maintain active roadside water quality program. | [11 empty] | 0
Working with county toward improved roadside management. | TS: 6; JS: 4; YBC: 5; Ken: 1 |  |  | 16
5. Implement Ag Water Quality Management Plan in watershed.
Provide quarterly reports for Oregon Dept. of Agriculture that track efforts. | TS: 2; DB: 1; DO: 1; MC: 6; ALF: 2 |  |  | 12
Follow-up on landowner natural resource concerns (i.e. complaints). | TS: 4; DO: 1; MC: 6; ALF: 1 |  |  | 12
Administer LMA funds and track LMA progress, submit project summaries | TS: 1; DO: 1; MC: 4; ALF: 1 |  |  | 7
Review the LMA SB1010 Plan | [9 empty] | 1 | bar: TS; MC; Ken
Coordinate perennial rye-grass erosion working group | MC: 5
Un-anticipated work involving ag water quality plan. | TS: 1; DO: 1; MC: 1.5; ALF: 1 |  |  | 4.5
Subtotal Goal 4 - Watersheds | 35 | 10 | 9 | 26.5 | 9 | 188 | 174 | 7 | 0 | 35 | 39 | 521.5
Staffing Priority Count | DB: WORK LOAD ANALYSIS | SWCD |  | Total
| TS | DB | DO | MC | ALF | JS | YBC | Ken | Kim | Board | Others
Goal #1 Provide conservation assistance. | 112 | 51 | 140 | 164 | 183 | 16 | 0 | 173 | 186 | 22 | 185 | 1232
Goal #2 Provide education and outreach. | 44 | 64 | 32 | 29 | 23 | 14 | 0 | 15 | 6 | 44 | 58 | 329
Goal #3 Sound District Operations. | 42 | 106 | 20 | 5 | 11 | 3 | 0 | 13 | 2 | 94 | 34 | 330
Goal #4 Watershed Planning and project implementation. | 35 | 10 | 9 | 26.5 | 9 | 188 | 174 | 7 | 0 | 35 | 39 | 532.5
SUBTOTAL PRIORITY DAYS | 233 | 231 | 201 | 224.5 | 226 | 221 | 174 | 208 | 194 | 195 | 316 | 2423.5
VACATION/SICK LEAVE | 13 | 15 | 19 | 19.5 | 12 | 15 | 12 | 25 | 12 |  |  | 142.5
TRAINING/CONFERENCES | 4 | 4 | 4 | 5 | 4 | 7 | 7 | 8 | 5 |  |  | 48
LEGAL HOLIDAYS | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 90
TOTAL WORKDAYS ACCOUNTED FOR | 260 | 260 | 234 | 259 | 252 | 253 | 203 | 251 | 221 |  |  | 2193
LESS TOTAL WORKDAYS IN ONE YEAR | 260 | 260 | 234 | 260 | 260 | 260 | x | 260 | 260
Days Remaining FOR 2005/2006 Workplan For Contingency | 0 | 0 | 0 | 1 | 8 | 7 | x | 9 | 39
%
TS =Tim Stieber, District Manager | TS: Breakdown of Staff Work Tasks; WORK LOAD ANALYSIS Ken: TS; WORK LOAD ANALYSIS Kim: DB | DO | MC | ALF | Avg
DB = Dalena Belden, Adminstrative Assistant | TS: Goal #1 Provide conservation assistance.; WORK LOAD ANALYSIS Ken: 43.08%; WORK LOAD ANALYSIS Kim: 19.62% | 59.83% | 63.32% | 72.62% | 51.69%
DO= Dean O'Reilly, Conservationist Technician | TS: Goal #2 Provide education and outreach.; WORK LOAD ANALYSIS Ken: 16.92%; WORK LOAD ANALYSIS Kim: 24.62% | 13.68% | 11.2% | 9.127% | 15.11%
RC = Michael Crabtree, Resource Conservationist | TS: Goal #3 Sound District Operations.; WORK LOAD ANALYSIS Ken: 16.15%; WORK LOAD ANALYSIS Kim: 40.77% | 8.547% | 1.931% | 4.365% | 14.35%
ALF = Amie Loop-Frison, Resource Conservationist | TS: Goal #4 Watershed Planning/ projects.; WORK LOAD ANALYSIS Ken: 13.46%; WORK LOAD ANALYSIS Kim: 3.846% | 3.846% | 10.23% | 3.571% | 6.991%
JS = Jamie Sheahan, Watershed Coordinator | TS: Other activities; WORK LOAD ANALYSIS Ken: 10.38%; WORK LOAD ANALYSIS Kim: 11.15% | 14.1% | 13.32% | 10.32% | 11.86%
YBC = Yamhill Basin Council | WORK LOAD ANALYSIS Ken: 100%; WORK LOAD ANALYSIS Kim: 100% | 100% | 100% | 100%
NRCS - Ken Hale, District Conservationist
NRCS - Kim Hudnall, Soil Conservationist
Board - Yamhill Soil and Water Conservation Board
X = WILL BE INVOLVED BUT NOT COMMITTTED TO ACTIVITY